Azure Disaster Recovery

Planning & Implementation Guide

A step-by-step structured plan for architects, engineers, and decision-makers

Covers:  Workload inventory · SLA baselines · Landing zone design · Single-region HA · Cross-region DR · Networking & identity · Testing & operations

Scope: VMs · App Service · SQL Database / Managed Instance · Azure Blob Storage · Azure Files · AI Foundry · Application Gateway · Azure Firewall

# How to use this document

This guide is structured as a linear, phased journey. Each phase builds on the previous one — do not skip to Phase 5 (DR region) before completing Phase 4 (single-region HA), as weaknesses in the primary will replicate to your DR environment.

Each phase contains:

- Numbered steps with descriptions

- A concrete deliverable for each step — if you cannot produce it, the step is not done

- Reference tables to support decision-making

Work through each phase with your team. Use the deliverables as sign-off gates before moving forward.

PHASE 1 Foundations and discovery

Understand what you have before planning where you are going.

Objective: build a complete workload inventory and get business sign-off on RTO/RPO targets before touching any infrastructure.

| 1.1 | Inventory all workloads Create a spreadsheet listing every application, database, storage account, and AI Foundry deployment. Record the owner, business function, dependent services, and data classification (public / internal / confidential / regulated). Deliverable: Workload inventory spreadsheet PLANNING |
| --- | --- |

| 1.2 | Define RTO and RPO per workload Ask the business: how long can this service be down (RTO)? How much data loss is acceptable in a disaster (RPO)? These are business decisions, not technical ones. Classify each workload into Tier 1, 2, or 3 using the table below. Deliverable: RTO/RPO matrix signed off by stakeholders PLANNING |
| --- | --- |

| 1.3 | Understand Azure paired regions and select your DR target Azure pairs each region with a designated partner for platform update staggering, and GRS/GZRS storage always replicates to the paired region. Your DR deployment should target the paired region wherever possible. See the paired region reference table below. Deliverable: Confirmed primary region + DR paired region selection PLANNING |
| --- | --- |

| 1.4 | Assess and approve DR budget Determine whether you can fund: (A) Full warm standby — full compute running in DR at all times; (B) Pilot Light — only networking and identity in DR, compute deployed from IaC on failover; or (C) Backup-only cold DR — no compute, restore from backup on demand. This decision gates every subsequent architecture choice. Deliverable: DR budget envelope approved and documented PLANNING |
| --- | --- |

## Workload tier classification

| Tier 1 — Mission critical RTO < 1 hour RPO ~0 (seconds) Active-active or hot standby. ASR + SQL Failover Group + GZRS + Front Door auto-failover. | Tier 2 — Business important RTO 4–8 hours RPO < 1 hour Pilot Light with IaC redeploy, ASR, Backup-based restore + manual failover runbook. | Tier 3 — Non-critical RTO 24–72 hours RPO 24 hours Cold DR. Geo-redundant backups only. Restore on demand to DR region. |
| --- | --- | --- |

## Azure paired regions reference

| Primary region | Azure paired region (DR target) |
| --- | --- |
| UAE North (Abu Dhabi) | UAE Central (Dubai) |
| East US | West US |
| East US 2 | Central US |
| North Europe | West Europe |
| UK South | UK West |
| Southeast Asia | East Asia |
| Australia East | Australia Southeast |

PHASE 2 SLA baseline and availability options

Know what Azure guarantees before designing your high-availability configuration.

Objective: identify the SLA gap between your current configuration and the maximum achievable SLA for each resource type.

| 2.1 | Review the SLA table and identify gaps Map every resource in your workload inventory to its current SLA tier and the maximum achievable SLA with zone redundancy enabled. Document the delta — this is your HA improvement backlog. Deliverable: SLA gap analysis: current vs target per resource PLANNING |
| --- | --- |

| 2.2 | Plan zone redundancy for each service VMs: deploy across zones 1/2/3 with a Standard Load Balancer. App Service: PremiumV2+ with minimum 3 instances and zone redundancy enabled. SQL DB: Business Critical tier with zone redundancy. Storage: upgrade LRS to ZRS or GZRS. Application Gateway v2 and Azure Firewall: zone-redundant SKU across all 3 zones. Deliverable: Zone redundancy design documented per service INFRASTRUCTURE |
| --- | --- |

| 2.3 | Storage redundancy: choose the right tier Azure Blob Storage and Azure Files share the same redundancy model. LRS (3 copies, 1 datacenter) for dev/test only. ZRS (3 zones, 1 region) for production. GZRS (zones + geo) for production with DR. Enable RA-GZRS to get a readable secondary endpoint at all times — no infrastructure to manage, just a URL suffix change. Deliverable: Storage account redundancy plan documented per account INFRASTRUCTURE |
| --- | --- |

## SLA reference table

| Resource | Single instance | Avail. set/zones | Zone redundant (max SLA) |
| --- | --- | --- | --- |
| Virtual machine | 99.9% | 99.95% (Avail. Set) / 99.99% (Zones) | 99.99% |
| App Service | 99.95% | 99.99% (PremiumV2+, 3 zones) | 99.99% |
| SQL Database (BC) | 99.99% | 99.99% | 99.99% |
| SQL Managed Instance (BC) | 99.99% | 99.99% | 99.99% |
| Storage (ZRS) | 99.9% (LRS) | 99.9999% (ZRS/GZRS) | 99.9999% |
| Application Gateway v2 | — | 99.95% | 99.95% |
| Azure Firewall Premium | — | 99.99% | 99.99% |
| Azure AI Foundry | Varies | Inherited from OpenAI/Cognitive Svc | 99.9%+ |
| Azure Blob / Files | 99.9% (LRS) | 99.9999% (ZRS) | 99.9999% (GZRS) |

PHASE 3 Landing zone and subscription design

Build the governance and structural foundation before deploying workloads.

Objective: establish a well-governed Azure environment using the ALZ accelerator and a clean subscription structure.

| 3.1 | Deploy Azure Landing Zone (ALZ) Use the ALZ Accelerator (available as Bicep or Terraform at aka.ms/alz) to deploy the management group hierarchy: Root > Platform > Workloads > Sandbox. This gives you policy inheritance, RBAC, centralized logging, and audit by default. Do not build this structure manually — the accelerator encodes years of proven patterns. Deliverable: ALZ management group hierarchy deployed and verified INFRASTRUCTURE |
| --- | --- |

| 3.2 | Create subscriptions by function Management subscription: Azure Monitor, Defender for Cloud, Log Analytics workspace. Connectivity subscription: hub VNets, ExpressRoute/VPN gateways, Azure Firewall — for BOTH primary and DR regions. Identity subscription: AD DS VMs, Entra Domain Services. Workload subscriptions: one per team or application, separated by dev / staging / prod. Never mix environments in the same subscription. Deliverable: Subscription map with named owners and purpose documented INFRASTRUCTURE |
| --- | --- |

| 3.3 | Apply Azure Policy at management group level Enforce the following as deny or audit policies: require zone redundancy on supported resource types; require private endpoints for PaaS services; deny public IP creation on workload resources; require diagnostic settings to route to Log Analytics; enforce mandatory tagging (owner, environment, cost-center). Use parent + child policy structure so global rules apply everywhere and teams can layer environment-specific additions. Deliverable: Policy compliance report showing 100% on core policies SECURITY & GOVERNANCE |
| --- | --- |

| 3.4 | Define all infrastructure as code (IaC) Every resource must be reproducible from a Bicep or Terraform template. The DR region deployment should be a parameter change not a manual exercise. Store Terraform state in a geo-redundant storage account. Commit all IaC to a version-controlled repository with PR-based review gates. This is the single largest accelerator for recovery time. Deliverable: IaC repo with primary and DR region parameter configs checked in INFRASTRUCTURE |
| --- | --- |

## Recommended subscription layout

| Subscription | Purpose | Key resources |
| --- | --- | --- |
| Management | Governance, monitoring, security | Log Analytics, Defender, Monitor, Automation |
| Connectivity | Networking — both regions | Hub VNets, Firewall, App GW, ExpressRoute, VPN GW |
| Identity | Directory services | AD DS VMs, Entra Domain Services, Key Vault |
| Workload (prod) | Production applications | App VMs, App Service, SQL DB, Storage, AI Foundry |
| Workload (staging) | Pre-production testing | Staging slots, test databases |
| Workload (dev) | Developer environments | Dev resources, sandboxes |

PHASE 4 Single-region high availability

Before adding a second region, make the primary as resilient as possible.

Objective: eliminate single-datacenter as a failure domain using availability zones for every Tier 1 and Tier 2 workload.

| 4.1 | Deploy VMs across availability zones Pin VMs to zones 1, 2, and 3. Place a Standard Load Balancer (zone-redundant SKU) in front. For scalable workloads, use VM Scale Sets with zone balance enabled. Zone redundancy removes a single datacenter's power, cooling, or network failure as a service-impacting event. Deliverable: All Tier 1 VMs verified zone-redundant in Azure portal INFRASTRUCTURE |
| --- | --- |

| 4.2 | Configure App Service zone redundancy Upgrade to PremiumV2 or PremiumV3 App Service Plan. Set minimum instance count to 3 (required for zone spread). Enable zone redundancy at plan creation — it cannot be changed after the fact. Use deployment slots for zero-downtime releases; they do not affect SLA on their own. Deliverable: App Service plan showing zone redundancy enabled in properties blade INFRASTRUCTURE |
| --- | --- |

| 4.3 | Upgrade SQL to Business Critical and enable zone redundancy Business Critical tier includes a built-in read-only replica in the same region, faster automatic failover (20–30 seconds), and zone redundancy support. For SQL Managed Instance, enable zone redundancy on the Business Critical tier via the portal or IaC. The in-region read replica is a free standby — use it for reporting to reduce load on the primary. Deliverable: SQL tier confirmed as Business Critical, zone redundancy on, read replica accessible INFRASTRUCTURE |
| --- | --- |

| 4.4 | Deploy Application Gateway and Azure Firewall zone-redundant Application Gateway v2 (WAF): select all 3 zones at deployment, set min scale units to 2 to prevent cold-start latency. Azure Firewall Premium: deploy with zones 1, 2, 3 in the hub VNet. Apply a Firewall Policy (not classic rules) the policy can be shared with or linked to the DR Firewall, keeping one rule set across both regions. Deliverable: App GW and Firewall zone-pinned in hub VNet, Firewall Policy attached INFRASTRUCTURE |
| --- | --- |

| 4.5 | Set storage redundancy to ZRS or GZRS For all Azure Blob and Azure Files production accounts: migrate from LRS to ZRS (same region, 3 zones) or GZRS (zones + geo-replication). Enable RA-GZRS to get a readable secondary endpoint at all times. The secondary endpoint URL is: {account}.blob.core.windows.net -> {account}-secondary.blob.core.windows.net. No infrastructure to deploy — just a redundancy configuration change. Deliverable: All production storage accounts set to GZRS or ZRS; secondary endpoints verified INFRASTRUCTURE |
| --- | --- |

PHASE 5 DR region and replication tools

Extend to the paired region using the right replication tool for each workload tier and service type.

Objective: configure and validate replication to the DR region for all Tier 1 and Tier 2 workloads, with appropriate budget-constrained alternatives for Tier 3.

| 5.1 | Configure Azure Site Recovery (ASR) for Tier 1 VMs Enable ASR replication for each Tier 1 VM targeting the paired region. Configure Recovery Plans with failover ordering: domain controllers first, then databases, then application tier, then front end. ASR delivers RPO as low as 30 seconds. Run a test failover into an isolated VNet quarterly — it does not affect production. Set replication policy to retain recovery points for at least 24 hours. Deliverable: ASR replication enabled for all Tier 1 VMs; first test failover completed and documented INFRASTRUCTURE |
| --- | --- |

| 5.2 | Create SQL Failover Groups For SQL Database: create a failover group spanning primary and DR regions. Your application connection string points to the group listener endpoint — Azure redirects transparently on failover with no connection string change required. For SQL Managed Instance: provision a secondary MI in the DR region and join the same failover group. RPO is under 5 seconds for Business Critical tier. Test with a planned failover (no data loss) before relying on it for DR. Deliverable: Failover group created and tested with a planned failover; application connection string updated to listener endpoint INFRASTRUCTURE |
| --- | --- |

| 5.3 | Storage: RA-GZRS + AzCopy for bulk or scripted migrations RA-GZRS handles ongoing replication automatically — no action needed after enabling it. For one-time large data migrations between storage accounts across regions, use AzCopy with the --recursive flag for server-side copy (no local bandwidth consumed). For Azure Files ongoing multi-site sync, use Azure File Sync agents or Azure Storage Mover for managed cloud-to-cloud copy. Deliverable: RA-GZRS secondary endpoint read-tested; AzCopy scripts for any required one-time migration documented INFRASTRUCTURE |
| --- | --- |

| 5.4 | Budget-constrained option: Pilot Light DR pattern If full warm standby is unaffordable, deploy only the following in the DR region at all times: hub VNet with Firewall and gateway (networking baseline), at least one domain controller VM or Entra DS replica set (identity baseline), and a Key Vault populated with secrets (secret baseline). Do not run application VMs or App Service plans until failover is declared. On failover, execute your IaC pipeline to deploy compute into the pre-warmed network. This pattern reduces ongoing DR cost by approximately 80% vs full warm standby while significantly improving RTO over pure cold DR. Deliverable: Pilot-light infrastructure deployed in DR region; spin-up time measured and documented in runbook PLANNING |
| --- | --- |

| 5.5 | AI Foundry: cross-region endpoint routing Deploy AI Foundry projects in the DR region or place Azure API Management in front of two regional Azure OpenAI endpoints. APIM health probes will automatically route to the DR endpoint if the primary is unavailable. For Tier 1 AI workloads, provision PTU (provisioned throughput) capacity in both regions so quota is not the bottleneck during failover. Deliverable: AI endpoints deployed and verified in both regions; APIM routing tested INFRASTRUCTURE |
| --- | --- |

| 5.6 | Configure Azure Front Door for global HTTP failover Deploy Azure Front Door above your Application Gateways in both primary and DR regions. Front Door health probes detect primary Application Gateway failure and shift traffic to the DR origin automatically, typically within 30–60 seconds. Apply a Front Door WAF policy so security rules are enforced globally regardless of which origin is serving traffic. Deliverable: Front Door failover tested by disabling primary origin health probe temporarily INFRASTRUCTURE |
| --- | --- |

## Azure replication tools reference

| Tool / feature | Applies to | Key capability |
| --- | --- | --- |
| Azure Site Recovery (ASR) | VMs, physical servers | 30 sec RPO, full recovery plans, test failover into isolated VNet |
| SQL Failover Groups | SQL DB, SQL Managed Instance | Transparent failover, same connection string, RPO < 5 sec (BC) |
| SQL Always On AG | SQL on VMs | Manual or automatic failover, synchronous or async replica |
| GZRS / RA-GZRS | Azure Blob, Azure Files, Queues, Tables | Built-in async geo-replication, RA gives read access to secondary |
| AzCopy | Blob, Files — one-time or scripted sync | Server-side copy, SAS-authenticated, recursive sync |
| Azure File Sync | Azure Files (on-prem + cloud) | Ongoing multi-site sync, cloud tiering |
| Storage Mover | Cloud-to-cloud file migration | Managed service for large-scale copy between storage accounts |
| Azure Backup + CRR | VMs, SQL, Files, AKS | Cross-Region Restore from paired region, cold DR safety net |
| Azure API Management (multi-region) | APIs / AI Foundry endpoints | Active-active or active-passive with auto health routing |
| Cosmos DB multi-region write | Cosmos DB | Turnkey — add DR region in portal, near-zero RPO |

PHASE 6 Networking and identity

Ensure connectivity and access survive a regional failure they are the foundation everything else depends on.

Objective: validate that network paths and identity services are resilient in both regions and that DNS, secrets, and access controls are pre-configured for the DR environment.

| 6.1 | ExpressRoute primary + S2S VPN failover Deploy both an ExpressRoute gateway and a VPN gateway in your primary hub VNet. Configure the S2S VPN with the same BGP prefixes at a lower LOCAL_PREF value (or higher AS path length) so it is only preferred when ExpressRoute is unavailable. Azure's BGP routing will automatically prefer ExpressRoute; the VPN activates within seconds of a BGP session drop. In the DR region, deploy the same dual-gateway pattern with a separate ExpressRoute circuit or VPN tunnel from a different on-premises router. Deliverable: VPN failover tested by simulating ExpressRoute BGP drop; recovery time measured INFRASTRUCTURE |
| --- | --- |

| 6.2 | Hub-spoke topology in both regions Primary hub VNet contains: Azure Firewall, Application Gateway, ExpressRoute/VPN gateway, Azure Bastion. Spoke VNets connect to the hub via VNet peering for workloads. Mirror this structure in the DR region. Use non-overlapping IP address space (e.g. primary: 10.0.0.0/8, DR: 10.128.0.0/8). Enable global VNet peering between primary hub and DR hub for cross-region private connectivity during failover tests. Deliverable: Hub-spoke topology deployed in both regions; global VNet peering confirmed active INFRASTRUCTURE |
| --- | --- |

| 6.3 | Private DNS Zones — link to both regions Every private endpoint (storage, SQL DB, Key Vault, Service Bus, App Service, AI Foundry) needs a DNS record in the corresponding private DNS zone (e.g. privatelink.blob.core.windows.net). Link each DNS zone to hub VNets in both primary and DR regions. Test DNS resolution explicitly from DR VMs — run nslookup or Resolve-DnsName for each private endpoint before you need to failover. Deliverable: DNS resolution tested from DR VNet for all private endpoint resource types INFRASTRUCTURE |
| --- | --- |

| 6.4 | Entra ID and domain controllers in DR region Entra ID (Azure AD) is globally redundant — no action required. For Entra Domain Services: add a replica set in the DR region via the portal (Settings > Replica sets). For AD DS on VMs: deploy at least one domain controller VM in the DR region, either managed by ASR replication or deployed from a golden image. Define all RBAC assignments and managed identity role assignments in IaC so they are automatically reproduced when resources are deployed in the DR region. Deliverable: DR domain controller validated; RBAC and managed identity assignments confirmed in IaC SECURITY |
| --- | --- |

| 6.5 | Key Vault in DR region and secret synchronization Deploy a dedicated Key Vault in the DR region with soft delete and purge protection enabled. Implement a secret sync pipeline triggered by Key Vault events in the primary — when a secret is created or updated, the pipeline replicates it to the DR vault. Applications reference Key Vault via managed identity (never hardcoded credentials or connection strings). Validate that DR workloads can successfully retrieve secrets from the DR vault before declaring the environment ready. Deliverable: DR Key Vault populated and verified; application managed identity access confirmed SECURITY |
| --- | --- |

| 6.6 | DDoS Protection and Firewall Policy in DR Enable Azure DDoS Network Protection on the DR hub VNet (it is region-scoped — the primary's protection does not extend to DR). Link the existing Firewall Policy to the DR Azure Firewall so rule changes made in the primary automatically apply to DR. If using child policies for environment-specific rules, create the equivalent child policy in the DR region. Deliverable: DDoS Protection enabled on DR hub VNet; Firewall Policy linked and rules verified SECURITY |
| --- | --- |

PHASE 7 Validate, monitor, and operate

A disaster recovery plan that has never been tested is not a disaster recovery plan.

Objective: prove that the plan works before you need it, then maintain visibility over replication health and readiness on an ongoing basis.

| 7.1 | Enable Microsoft Defender for Cloud across all subscriptions Enable Defender for Cloud on every subscription. Configure it to send alerts for: ASR replication health degradation, SQL failover group lag, storage account availability drops, and Key Vault access anomalies. Target a Secure Score above 80% in both primary and DR subscriptions. Defender for Cloud will surface misconfigured resources in the DR environment that could leave you exposed during an actual failover. Deliverable: Defender for Cloud Secure Score above 80% in all subscriptions; key DR alerts configured SECURITY |
| --- | --- |

| 7.2 | Centralized monitoring with Log Analytics Deploy one Log Analytics workspace in the Management subscription. Route diagnostic settings from all resources in both primary and DR regions into this single workspace. Create Azure Monitor Alert rules for: ASR RPO exceeding threshold, SQL failover group health state changes, ExpressRoute/VPN BGP session drops, storage account availability below SLA, Firewall rule hit anomalies. Configure action groups with email, SMS, and Teams/Slack webhook notifications. Deliverable: Alert dashboard live; action groups tested with a manual alert trigger OPERATIONS |
| --- | --- |

| 7.3 | Write the failover runbook Document step-by-step: who has authority to declare a DR event; the exact failover order (domain controllers > databases > application tier > front end > DNS cutover); how DNS is updated; how users and customers are notified; how to validate each service after failover. Include failback steps — returning to the primary region after it recovers is a separate procedure and equally important. Automate as many steps as possible using Azure Automation Runbooks or GitHub Actions workflows. Deliverable: Runbook published in shared wiki; reviewed and signed off by all workload owners OPERATIONS |
| --- | --- |

| 7.4 | Run a full DR drill at least quarterly ASR test failover: initiate from the Recovery Services vault into an isolated VNet — production is not affected. SQL planned failover: trigger a planned failover to the DR region and back, measuring actual failover time. End-to-end application test: validate that the application functions correctly end-to-end from the DR region, including authentication, data access, and integrations. Measure actual RTO and RPO achieved and compare to targets. Update the runbook with lessons learned after every drill. Deliverable: Drill report with measured RTO/RPO vs target; runbook updated with findings TESTING |
| --- | --- |

| 7.5 | Configure Azure Backup Center Centralize backup policy management across all subscriptions in Azure Backup Center. Verify that Tier 1 and Tier 2 workloads use GRS backup vaults (not LRS) so backup data is replicated to the paired region. Enable Cross-Region Restore (CRR) for VMs so they can be restored from the DR region independently of ASR. Confirm retention periods meet or exceed your RPO targets for each workload tier. Deliverable: Backup Center dashboard showing zero policy compliance gaps; CRR tested for at least one VM OPERATIONS |
| --- | --- |

# Appendix A: workload DR decision framework

Use the following decision tree to determine the correct DR strategy per workload. Not every workload requires cross-region replication that choice should be driven by business requirements, not by default.

| Workload example | RTO target | RPO target | DR strategy | Key tools |
| --- | --- | --- | --- | --- |
| Customer-facing e-commerce / payments | < 15 min | ~0 | Active-active (2 regions) | Front Door, SQL FG, GZRS |
| Core internal ERP / HR system | < 1 hour | < 5 min | Hot standby (ASR managed) | ASR, SQL FG, GZRS |
| Internal reporting / analytics | 4–8 hours | < 1 hour | Pilot light | ASR or IaC redeploy, Backup CRR |
| AI Foundry / ML workloads | < 2 hours | < 30 min | API GW routing + secondary endpoint | APIM, OpenAI PTU in 2 regions |
| Dev / test environments | 24–72 hours | 24 hours | Cold DR — backup only | Azure Backup, geo-redundant vault |
| Archive / compliance storage | 72+ hours | 24 hours | RA-GZRS + Backup | GZRS, immutability policy |

# Appendix B: implementation checklist

Use this checklist as a quick sign-off tracker. Each item maps to a step in the phased plan above.

## Phase 1 — Foundations

- [ ] Workload inventory spreadsheet completed and reviewed

- [ ] RTO/RPO matrix signed off by business stakeholders

- [ ] Primary and DR paired region confirmed

- [ ] DR budget approved (warm standby / pilot light / cold DR)

## Phase 2 — SLA baseline

- [ ] SLA gap analysis completed for all resource types

- [ ] Zone redundancy design documented per service

- [ ] Storage redundancy tier selected and documented per account

## Phase 3 — Landing zone

- [ ] ALZ accelerator deployed and management group hierarchy verified

- [ ] Subscriptions created by function with named owners

- [ ] Azure Policy applied at management group level; compliance verified

- [ ] IaC repository established for primary and DR region configs

## Phase 4 — Single-region HA

- [ ] All Tier 1 VMs deployed across availability zones

- [ ] App Service plans on PremiumV2+ with zone redundancy and 3+ instances

- [ ] SQL upgraded to Business Critical with zone redundancy enabled

- [ ] Application Gateway v2 and Azure Firewall zone-redundant with Firewall Policy

- [ ] All production storage accounts set to GZRS or ZRS

## Phase 5 — DR region and replication

- [ ] ASR replication enabled for all Tier 1 VMs; first test failover completed

- [ ] SQL Failover Groups created and tested with planned failover

- [ ] RA-GZRS secondary endpoints verified; AzCopy scripts documented

- [ ] Pilot-light infrastructure deployed in DR region (if applicable)

- [ ] AI Foundry endpoints deployed and verified in both regions

- [ ] Azure Front Door configured for automatic failover; tested

## Phase 6 — Networking and identity

- [ ] ExpressRoute + S2S VPN failover tested by simulating BGP drop

- [ ] Hub-spoke topology deployed in DR region; global VNet peering active

- [ ] Private DNS Zones linked to both region hub VNets; DNS resolution tested

- [ ] DR domain controller deployed and validated

- [ ] DR Key Vault populated; application managed identity access confirmed

- [ ] DDoS Protection enabled on DR hub VNet; Firewall Policy linked

## Phase 7 — Validate and operate

- [ ] Defender for Cloud Secure Score above 80% in all subscriptions

- [ ] Centralised Log Analytics workspace; alert rules and action groups active

- [ ] Failover runbook published, reviewed, and signed off by all owners

- [ ] Full DR drill completed; actual RTO/RPO measured vs target

- [ ] Azure Backup Center showing zero policy gaps; CRR tested

# Appendix C: glossary

| Term | Definition |
| --- | --- |
| RTO | Recovery Time Objective — the maximum acceptable time a service can be unavailable after a disaster. |
| RPO | Recovery Point Objective — the maximum acceptable amount of data loss measured in time (e.g. 30 minutes of transactions). |
| ASR | Azure Site Recovery — Microsoft's managed VM replication and orchestration service for DR failover. |
| ALZ | Azure Landing Zone — Microsoft's proven architecture pattern for a well-governed, multi-subscription Azure environment. |
| GZRS | Geo-Zone-Redundant Storage — storage redundancy combining zone redundancy in the primary region with geo-replication to the paired region. |
| RA-GZRS | Read-Access GZRS — GZRS with a publicly accessible read endpoint in the secondary region, active at all times. |
| Failover Group | Azure SQL feature that provides transparent failover of one or more databases to a secondary region via a listener endpoint. |
| Pilot Light | A DR pattern where only the minimal infrastructure (networking, identity) runs in the DR region; compute is deployed from IaC on failover. |
| Paired region | A designated Azure region partner for update staggering, GRS replication target, and prioritised recovery in platform-wide outages. |
| AzCopy | Microsoft's CLI tool for high-performance, server-side blob and file copy between storage accounts. |
| Hub-spoke | A network topology where a central hub VNet (containing shared services) connects to multiple spoke VNets (containing workloads) via peering. |
| CRR | Cross-Region Restore — Azure Backup feature enabling restore of backup data from a secondary paired region. |
| Entra ID | Microsoft's cloud-based identity and access management service (formerly Azure Active Directory). |
| Firewall Policy | An Azure resource that centralises Azure Firewall rules, allowing one policy to be linked across multiple Firewall instances. |
| IaC | Infrastructure as Code — the practice of managing infrastructure through machine-readable configuration files (Bicep, Terraform, ARM). |